## Slide 1
Release Management
Title

## Slide 2: Release Criteria
Simple
Increment | Theme | Criteria | Verification Method (critical V&V steps)
Increment 1 | Precision | 20% reduction in false positives when compared to manual testing. | Compare the number of false positives from automated tests to historical data from manual tests. Calculate the percentage reduction and confirm it meets the 20% target.
 |  | 100% pass rate for the results of automated tests when compared with historical manual test results (test strategy theme: precision) | Generate detailed reports from both automated and historical manual tests. Perform a side-by-side comparison of test results, focusing on critical test cases. Log discrepancies as bugs in Bugzilla for further analysis. Resolve all discrepancies to ensure 100% resolution rate.
 |  | 100% pass rate for integration tests of integrate Selenium with Jenkins CI/CD for the 120 manual tests (test strategy theme: efficiency) | Verify Jenkins pipeline configuration to ensure Selenium scripts for the 120 manual tests are integrated. Run a set of test scripts through the CI/CD pipeline and success rate of execution will be recorded in Detailed test result reports using TestRail. Track and resolve 100% any integration issues in Bugzilla.
 | Efficiency | Achieve a 50% reduction in execution time for Selenium Grid tests across multiple browsers compared to initial setup. | Configure Selenium Grid for parallel testing and execute tests. Monitor and document the initial and optimized execution times and resource usage. Calculate the percentage reduction in execution time and confirm it meets the 50% target.
 |  | Reduce the setup and automated test execution time for 120 automated unit tests and 30 manual unit tests to a total of 72 hours. | Track and record the total setup and execution time for all 150 tests. Ensure the combined time for setup and execution does not exceed 72 hours. Compare the setup and execution times to previous benchmarks and log delays and issues in Bugzilla. Calculate and verify the setup time reduction to meet the 72-hour target.

## Slide 3: Release Checklist （Focus: Increment 1）
Simple
Test Strategy Theme | Criteria | Artifact | Responsible | Accountable | Consulted | Informed
Precision | 20% reduction in false positives when compared to manual testing | Comparison report with history data | Brian Tran (IT DevTester) | Jamie Teller (DevOps Engineer) | Krista Adams (Product Engineer) | Alex Hart (Security Manager)
 | 100% pass rate for the results of automated tests when compared with historical manual test results | Detailed reports from automated and historical tests | Brian Tran (IT DevTester) | Jamie Teller (DevOps Engineer) | Krista Adams (Product Engineer), Security Manager | Jennifer Clark (SOC Analyst)
 |  | Side-by-side comparison document | Brian Tran (IT DevTester) | Jamie Teller (DevOps Engineer) | Krista Adams (Product Engineer), Security Manager | Jennifer Clark (SOC Analyst)
 | 100% pass rate for integration tests of Selenium scripts with Jenkins CI/CD for the 120 manual tests | Detailed test result reports using TestRail | Brian Tran (IT DevTester) | Jamie Teller (DevOps Engineer) | Krista Adams (Product Engineer), Security Manager | Jennifer Clark (SOC Analyst)
Efficiency | Achieve a 50% reduction in execution time for Selenium Grid tests across multiple browsers compared to initial setup | Initial execution time report | Jamie Teller (DevOps Engineer) | Jamie Teller (DevOps Engineer) | Brian Tran (IT DevTester) | Krista Adams (Product Engineer)
 |  | Optimized execution time report | Jamie Teller (DevOps Engineer) | Jamie Teller (DevOps Engineer) | Brian Tran (IT DevTester) | Krista Adams (Product Engineer)
 | Reduce the setup and automated test execution time for 120 automated unit tests and 30 manual unit tests to a total of 72 hours. | Execution time summary | Brian Tran (IT DevTester) | Jamie Teller (DevOps Engineer) | Krista Adams (Product Engineer) | Alex Hart (Security Manager)

## Slide 4: Version Policy
VERSION Key Factors:[1,2]
  Traceable with BUILD. BUILD is coupled with product development or test engineering build farm (files, directories; packages, modules, functions/procedures; components, containers; subsystems).
  CyberSIEM build farm is structured into THREE directories: PRECISION, EFFICIENCY, SECURITY, .
  Build Types: D for development build (unit tests); A for Alpha build; B for Beta build; S for System test build; R for regression test build; I for Integration Build; P for Performance test build; G for Production GOLDEN build.
VERSION Rules[3]:
  MAJOR.MINOR.DOTDOT.[P<PRECISION>,E<EFFICIENCY>,S<SECURITY>].[BUILD TYPE].[DEBUG BUILD OR NOT : D for debug, ND for non-debug].number [1-N]
  MAJOR starts from zero at the beginning of the project and ends with 1 when it’s ready to be fully integrated.
  During the intermediate sub-milestones, MINOR will have different numbers rounding up to 10 for different modules.
  Patch number changes when a new feature is added or modified. This is normally for small bug-fixes or the like.
Simple
[1] SemVer. 2020. Semantic Versioning 2.0.0. Retrieved June 3, 2024, from https://semver.org/
[2] Microsoft. 2024. Versioning. Retrieved June 3, 2024, from https://learn.microsoft.com/en-us/dotnet/standard/assembly/versioning
[3] Stack Overflow. 2024. What rules does software version numbering follow?. Retrieved June 3, 2024, from https://stackoverflow.com/questions/3826580/what-rules-does-software-version-numbering-follow

## Slide 5: Release Plan
Simple
Timeline | Jan | Feb | March | April | May | June
Increment/Release Version | V0.2.0 Increment 1 (Precision theme, development unit tests) | V0.3.0 Increment 1 (Efficiency theme, integration test) | V0.5.0 Increment 2 (precision/efficiency themes; alpha test, regression test) | V0.7.0 Increment 2 (Precision Theme; Beta Test) | V0.8.0 Increment 3 (Efficiency Theme; System/ Performance Test) | V1.0.0 Increment 3 (Security Theme; Golden Build Test)
Release Versions | V0.0.0.P.D.ND.7 V0.1.0.P.D.ND.5 | V.0.2.0.E.I.ND.3 V0.2.0.E.I.ND.6 | V0.3.0.E.A.ND.4 V0.4.0.P.R.ND.3 | V0.5.0.P.S.ND.5 V0.6.0.P.B.ND.3 | V0.7.0.E.S.ND.5 V0.7.0.E.P.ND.8 | V0.8.0.S.G.ND.3 V0.9.0.S.G.ND.5
Release Highlights | 40% Automated unit tests, Reduction in false positive testing, Precision testing against historical tests, Integration of Selenium with Jenkins CI/CD | Selenium Grid feature added, 33% reduced setup time to 48 hours | Over 95% regression test pass rate, 50% reduction in execution time to 48 hours for Selenium Grid tests across multiple browsers compared to initial execution time, 0 high severity bugs in test setup/execution | JUnit reporting feature added, 50% reduction in false positives rate with 97% precision, Beta testing | 75% reduction in test execution time to 24 hours compared to initial execution time, total turnaround time (setup & execution) is 72 hours | 0 control related security incidents, limit security incident response time to 1 hour
Key Contents | Test Script Set, False Positive Patch, Test result reports, Execution time summary | Selenium Grid configuration file, Setup time report | Jenkins Configuration, Regression test reports, Execution time summary | Selenium WebDriver configuration file, Beta test feedback and validation reports | Performance test reports, System test reports, Execution time summary | Security test reports